## BURNDOWN
Gráfico Burndown 2º Sprint
Atividades: | Horas previstas | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7 | Dia 8 | Dia 9 | Dia 10 | Dia 11 | Dia 12
Datas: |  | 2023-04-13 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-05-02 | 2023-05-03 | 2023-05-04
Inserir fotos na apresentação da equipe | 2 | bar: 2023-04-20; 2023-04-25
Reuniões diárias | 3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Inserir notas da 1º sprint no GitHub | 1 | bar: 2023-04-13
Registrar ferramentas utilizadas | 1 | 2023-04-13: 0.5
Readme.me com histórico do 1º print | 1.5 | 2023-04-13: 1; 2023-04-17: 0.5
Readme.me com histórico do 2º print | 1.5 | 2023-05-03: 1; 2023-05-04: 0.5
Registrar e organizar as tasks por sprint | 1.5
Adicionar contato da equipe | 0.5 | 2023-04-13: 0.5
Organizar e registrar task Sprint 2 | 3 | 2023-04-13: 1; 2023-04-18: 0.5; 2023-04-26: 1; 2023-05-02: 0.5
Ampliar a logo do grupo e o nome da equipe | 1 | bar: 2023-04-19
Colocar o tempo que vai utilizar pra fazer cada task! | 0.5 | 2023-04-24: 0.5
Inserir sprint backlog e product backlog no Github | 3 | 2023-04-17: 1; 2023-04-25: 0.5
Inserir no Github cópia da planilha de administração | 0.5 | 2023-04-20: 0.5
Rever, registrar e manter atualizados os commits | 3 | 2023-04-17: 0.5; 2023-04-18: 0.5; 2023-04-20: 0.5; 2023-04-24: 1; 2023-05-04: 0.5
Atualização do logo | 2 | 2023-04-26: 0.5; 2023-04-27: 0.5; 2023-05-02: 1
Criar hiperlinks de cada tópico. | 2 | 2023-04-18: 0.5; 2023-04-19: 0.5
Criar/atualizar gráfico Burndown | 4 | 2023-04-17: 0.5; 2023-04-19: 0.5; 2023-04-26: 1; 2023-05-03: 1; 2023-05-04: 2
Colocar cor de fundo claro | 1 | 2023-04-26: 0.5; 2023-04-27: 0.5
Criar a ideia do bolo para o texto | 2 | 2023-04-20: 1; 2023-04-25: 2
Elaborar perguntas para os questionários (formulários) | 3 | 2023-04-18: 1; 2023-04-24: 0.5; 2023-04-25: 0.5; 2023-05-02: 1
Criar atividades avaliativas: Mod. 1, 2 e 3. | 3 | 2023-04-27: 1.5; 2023-05-03: 1.5
Criar a pag. do módulo 1 em html . Tema: O que é Scrum? | 1 | 2023-04-18: 1; 2023-04-19: 0.5
Criar a pag. do módulo 2 em html. Tema: Os ingredientes do bolo | 1 | 2023-04-24: 0.5; 2023-04-26: 1
Conclusão de esboço do conteúdo Scrum, Módulos 1, 2 e 3. | 6 | 2023-04-13: 2; 2023-04-17: 2; 2023-04-18: 2
Criar a página do módulo 3 em html. Tema: Como fazer? | 1 | 2023-04-27: 0.5; 2023-05-04: 1
Criação material no Canva | 1 | bar: 2023-05-02
Criar o conteúdo do módulo 1 | 3 | 2023-04-20: 1.5; 2023-04-26: 1.5
Criar o conteúdo do módulo 2 | 3 | 2023-04-27: 1.5; 2023-05-03: 1.5
Criar o conteúdo do módulo 3 | 3 | 2023-04-27: 1.5; 2023-05-04: 1.5
Definir e registrar tasks Sprints 2 e 3 | 1 | 2023-04-13: 0.5; 2023-05-02: 0.5
Restante: | 60 | 53.25 | 48.5 | 42.75 | 40 | 35.25 | 32.5 | 28.25 | 22.5 | 16.25 | 12 | 6.75 | 1
Estimado: | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Note on A4: LAB-79: Aliceu Luiz
Note on A5: LAB-79: Todos
Note on A6: LAB-79: Diogo Luiz
Note on A7: LAB-79: Aliceu Lucas
Note on A8: LAB-79: Patrícia
Note on A9: LAB-79: Patrícia
Note on A10: LAB-79: Patrícia Lucas
Note on A11: LAB-79: Aliceu Diogo
Note on A12: LAB-79: Patrícia Diogo Luiz
Note on A13: LAB-79: Diogo Lucas
Note on A14: LAB-79: Todos
Note on A15: LAB-79: Aliceu
Note on A16: LAB-79: Luiz Patrícia
Note on A17: LAB-79: Todos
Note on A18: LAB-79: Lucas Diogo
Note on A19: LAB-79: Abner
Note on A20: LAB-79: Luiz
Note on A21: LAB-79: Lucas Murilo
Note on A22: LAB-79: Patrícia Raphael
Note on A23: LAB-79: Patrícia Raphael
Note on A24: LAB-79: Patrícia Raphael
Note on A25: LAB-79: Abner Lucas
Note on A26: LAB-79: Abner Lucas André Diogo
Note on A27: LAB-79: Raphael
Note on A28: LAB-79: Abner Lucas
Note on A29: LAB-79: Patrícia
Note on A30: LAB-79: Patrícia Raphael
Note on A31: LAB-79: Patrícia Raphael Murilo
Note on A32: LAB-79: Patrícia Raphael Murilo
Note on A33: LAB-79: Patrícia Luiz Diogo